Prompt1:

I want to open an online shop of selling school stationary items. I have 5 lakhs rupees to invest. Tell me the phases that I should invest money in so that my business gets successful. Just tell me the forest view of the phases and not the details.

Output

With an investment of ₹5 lakh, I recommend launching your online school stationery business in phases rather than spending the entire amount upfront. The goal is to validate demand, build a customer base, and scale only after you see sales.

Overview: Investment phases for your online stationery business

Phase 1 — Market Research & Business Planning

Identify target customers, demand, competitors, pricing, and sales channels.

Phase 2 — Initial Inventory & Supplier Setup

Select fast-moving stationery products and establish reliable suppliers.

Phase 3 — Online Store Setup

Build your store, product catalogue, payment system, and delivery process.

Phase 4 — Launch & Customer Acquisition

Start selling, test marketing channels, and attract your first customers.

Phase 5 — Performance Review & Optimisation

Measure sales, profit margins, repeat purchases, and inventory turnover.

Phase 6 — Expansion & Scaling

Expand successful product categories, increase inventory, and grow into additional sales channels.

Suggested allocation of your ₹5 lakh

| Investment area | Budget |
| --- | --- |
| Market research and planning | ₹25,000 |
| Initial inventory | ₹1,75,000 |
| Website and technology | ₹50,000 |
| Packaging and logistics setup | ₹40,000 |
| Marketing and launch | ₹75,000 |
| Working capital and contingency reserve | ₹1,35,000 |
| Total | ₹5,00,000 |

These are preliminary budget estimates, not fixed costs. Keep the working capital reserve protected until the business demonstrates consistent demand.

My recommendation: Start lean, launch with a focused range of fast-moving products, and release additional investment based on actual sales results rather than spending the entire budget at launch.

Prompt2:

Now tell me how to implement

“Phase 1 — Market Research & Business Planning

Identify target customers, demand, competitors, pricing, and sales channels.”

Budget is 25,000

Output

Phase 1: Market Research & Business Planning

Budget: ₹25,000 | Goal: Decide what to sell, whom to sell to, at what price, and where to sell.

For your online school stationery business in India, I would treat this phase as a short, structured research project. The objective is to reduce the risk of investing ₹5 lakh in products that customers may not buy.

1. Break the ₹25,000 into research activities

1. Customer research

₹5,000

Interview parents, teachers, tutors, and other potential buyers to understand purchasing habits and unmet needs.

2. Competitor research

₹4,000

Study prices, product ranges, delivery charges, customer reviews, and offers from competing sellers.

3. Supplier and pricing validation

₹4,000

Obtain supplier quotations, compare wholesale rates, and check samples and minimum order quantities.

4. Sales-channel testing

₹7,000

Test customer interest through a small online campaign, a simple product catalogue, or a landing page before building a full store.

5. Research tools and documentation

₹2,000

Organise findings, record prices, analyse responses, and prepare a business plan.

6. Contingency

₹3,000

Cover unexpected research expenses or additional product testing.

Total Phase 1 budget

₹25,000

2. Execute the phase in four weeks

Week 1

Understand customers

Interview around 20–30 potential buyers. Identify the products they buy regularly, typical order sizes, preferred brands, and what frustrates them about existing sellers.

Week 2

Study competition and suppliers

Compare 10–15 competitors and contact at least 5 suppliers. Shortlist products with competitive pricing and reliable availability.

Week 3

Test demand and channels

Test interest in selected stationery bundles and individual products. Compare potential channels such as your own website, marketplaces, and WhatsApp Business.

Week 4

Make the investment decision

Finalise the target customer, initial product range, selling prices, supplier shortlist, channel strategy, and launch budget.

3. What should you research specifically?

| Research area | Questions you must answer |
| --- | --- |
| Target customers | Parents buying for children, schools, tutors, or small businesses—which segment will you serve first? |
| Product demand | Which items sell frequently? Which school grades or age groups will you target? |
| Competition | How do competitors price products, deliver orders, and differentiate themselves? |
| Pricing | What are your landed costs, selling prices, marketplace fees, packaging costs, and delivery costs? |
| Sales channels | Should you start with a marketplace, your own website, WhatsApp, or a combination? |
| Profitability | Can you make a positive contribution after product, shipping, packaging, payment, and marketing costs? |

4. Deliverables required before moving to Phase 2

By the end of these four weeks, you should have:

- A clearly defined primary customer segment.

- A shortlist of approximately 20–30 products for further evaluation.

- A competitor comparison spreadsheet.

- Verified supplier quotations and sample evaluations.

- A preliminary pricing and unit-economics sheet.

- A preferred sales channel and initial marketing plan.

- A decision on whether to proceed, revise the business model, or test further.

Important: Do not treat survey responses or social media interest alone as proof of demand. Look for stronger evidence, such as actual purchases, paid pilot orders, or credible purchase commitments.

My recommendation is to keep this phase focused on answering one question: Is there a specific group of customers you can serve profitably with a focused range of school stationery products? Only then should you commit substantial money to inventory.

Now do the rest of the prompt

Prompt 3:

Now tell me how to implement

“Phase 2 — Initial Inventory & Supplier Setup

Select fast-moving stationery products and establish reliable suppliers.”

Budget is 1,75,000

Prompt 4:

Now tell me how to implement

“Phase 3 — Online Store Setup

Build your store, product catalogue, payment system, and delivery process.”

Budget is 50,000

Prompt 5:

Now tell me how to implement

“Phase 4 — Launch & Customer Acquisition

Start selling, test marketing channels, and attract your first customers.”

(And do the rest of the prompt)